UNITED STATES MARINE CORPS

## VOTING ACTION PLAN 2008-2009

# I.  PURPOSE

To implement the Federal Functions of the Uniformed and Overseas Citizens Absentee Voting Act (UOCAVA), administer the provisions of DoD Directive 1000.4 (Federal Voting Assistance Program (FVAP)), and MCO 1742.1A (Voter Registration Program), disseminate information and guidance, and coordinate tasks related to the Voter Registration Program.

II.  OBJECTIVE

To ensure that all Marines, their family members, Marine Corps civilian employees, and their authorized family members, who are absent from their voting residence, are provided all necessary voting information, including voting age requirements, election dates, Federal officers to be elected, constitutional amendments, other ballot proposals, and information on absentee registration and voting procedures.  This Voting Acton Plan does not supersede MCO 1742.1A.  The Voting Action Plan should be used in concert with MCO 1742.1A.

III.  TASKS

A.  Deputy Commandant for Manpower and Reserve Affairs shall:

1.  Ensure continuing command support to all levels of

the Voting Assistance Program.

2.  Coordinate and provide information concerning all

aspects of the Absentee Voter Registration Program.

3.  Establish and maintain the Marine Corps Voting

homepage.  The Voting homepage will provide specific

information regarding upcoming elections.

The Marine Corps Voting Homepage will also provide links

to all Marine Installation and Major Command Voting

Officers, links to other government voting websites,

including a link to the Federal Voting Assistance

Program website, and will also provide guidance for

ordering voting materials.

4.  Advertise the FVAP Workshop schedule throughout the

Marine Corps.

5.  File an “After Action Report” by 15 January 2009 to

the Director, FVAP, summarizing successes and/or

problems experienced in the conduct of the Voting

Program.

6.  Revise MCO 1742.1A or other procedural guidance on

voting assistance as necessary.

B.  Major Command Voting Officer (MCVO) shall:

1.  Ensure continuing command support at all levels of

the Voting Assistance Program.

2.  Coordinate and provide information concerning all

aspects of the Absentee Voter Registration Program.

3.  Ensure Voting Assistance Officer’s (VAO) are

appointed and trained at every level of command.

4.  Ensure commanders provide VAO’s adequate time to

perform VAO duties.  The MCVO is responsible for

coordinating the program with all subordinate units and

tenant commands.

5.  Ensure VAO designations are in writing.  When

Marines, including non-commissioned officers, are

designated as VAO’s, they are authorized to administer

oaths in connection with registration and voting.

6.  Ensure senior command support for FVAP training

workshops and orientations held at the installation,

emphasizing attendance of every VAO stationed at the

installation.  The host Installation Voting Assistance

Officer’s (IVAO) will invite VAO’s from tenant commands

and from nearby installations.  A senior officer,

Colonel or above, will be designated to represent the

installation/command and introduce the program.

7.  Performance as a VAO will be documented on the

Marines’ Fitness Report.  Commanders shall establish the

evaluation criteria for VAO’s performance within their

command.

8.  Ensure recruits are provided a Federal Post Cards

Application (FPCAs) for themselves and their voting age

dependents during recruit training.

9.  Ensure that all Marines receive at least one

briefing/training period, devoted to the absentee

voting process during recruit training and within all

leadership curricula, and again, in each year that

elections for federal office are held.  Emphasis should

be placed on the availability of voting information,

supporting materials, personal assistance, and the

importance of registering and voting.

10.  Ensure that special emphasis is given to the week

of August 31 - September 7, 2008, “Armed Forces Voting

Week” to encourage voters to register to vote.

11.  Ensure that special emphasis is given to the week

of October 12-18 2008, as “Absentee Voters Week” to

encourage voters to complete and mail their absentee

ballots so that they are received by local election

offices in time to be counted for the November general

election.

C.  Installation/Unit Voting Assistance Officers (IVAO/UVAO)

shall:

1.  Encourage and assist all eligible voters.

2.  Be readily available and equipped to provide

personal assistance to voters for federal, state, local,

and other jurisdictional elections during 2008-09.

Persons needing assistance in reading or understanding

any voting material will receive immediate assistance in

the appropriate language.

3.  Have a minimum of one UVAO assigned for every two

hundred Marines in the unit.

4.  Designate at least one well-advertised, fixed

location on the base, installation, or ship announcing

where absentee voting materials and assistance may be

obtained.  Locations may include Legal Assistance

Offices, Family Service Centers, and Community Centers.

5.  Attend a FVAP Workshop.  Workshops will be held

at military installations in the continental United

States and overseas locations.  If the VAO’s

installation is not scheduled to receive FVAP Workshop

training, VAO’s can attend training at any nearby

installation regardless of service hosting the training.

VAO’s stationed at remote locations can access the FVAP

website for training or request a training CD from the

SVAO.

6.  Conduct local training workshops during election

years for federal offices

7.  Ensure availability of FPCA’s for all eligible

voters.  Ensure delivery of FPCA’s is made in accordance

with MCO 1742.1A, ENCLOSURE 1, PAR 3.

8.  Ensure that Marines are afforded the opportunity to

complete FPCA’s upon checking-in/checking-out of their

respective unit and ensure sufficient copies of the FPCA

are included in orientation packets for new and

permanent change of station (PCS) personnel.  All

deployed personnel will be provided the opportunity to

complete a FPCA prior to deployment.

9.  Encourage access to the Marine Corps Web Site

(www.manpower.usmc.mil/voting) and the FVAP Web Site

(www.fvap.gov) to obtain voting information and

materials.  If internet access is not available, ensure

that voting information and related materials such as

the 2008-09 Voting Assistance Guide, and changes

thereto; necessary quantities of the FPCA, and Federal

Write-In Absentee Ballot (FWAB), are obtained and

disseminated in accordance with MCO 1742.1A.

10.  Recommend changes to command directives or

instructions on voting assistance as necessary.

11.  Provide for continuing evaluation of command voting

program.

12.  Ensure that special emphasis is given to the week

of August 31 - September 7, 2008, “Armed Forces Voting

Week” to encourage voters to register to vote.

13. Ensure that special emphasis is given to the week

of October 12-18 2008, as “Absentee Voters Week” to

encourage voters to complete and mail their absentee

ballots so that they are received by local election

offices in time to be counted for the November general

election.

D. Inspector-Instructors shall:

1.  Coordinate with the IVAO, MCVO and SVAO to maintain

a contingency Absentee Voting Program for reserve units

and personnel who have been activated and deployed.  The

contingency implementation Absentee Voting Program shall

ensure that all deployed personnel (Active and Reserve)

are able to exercise their absentee voting rights.  The

scope of the program should include the availability of

adequate supplies of the 2008-09 Voting Assistance

Guide, FPCAs and FWABs.

2.  Ensure a VAO is appointed within each activated

reserve unit to serve as a liaison with the IVAO, MCVO

and SVAO.

IV. SCHEDULE

A.  PHASE I:  Preparation and Initiation during Period of

September 1, 2007 – Spring 2008.

1.  Commanders at all levels of command shall encourage

access to the Marine Corps Voting Web Site

(www.manpower.usmc.mil/voting) and FVAP Web Site

(www.fvap.gov).  If Internet access is not available,

ensure that voting information and related materials

such as the 2008-2009 Voting Assistance Guide (VAG) and

necessary quantities of the FPCA and FWAB are obtained

and disseminated in accordance with MCO 1742.1A.

2.  Commanders at all levels of command shall ensure

procurement and distribution of FPCA’s and FWAB’s

through normal supply channels.

3.  Commanders at all levels of command shall provide

Installation telephone operators with the name, mailing

address, e-mail, and office telephone number of the MCVO

and IVAO by January 1, 2008.  The MCVO and IVAO shall

generate and maintain a directory containing names and

office telephone numbers of all local UVAO’s, including

tenant organizations, January 1, 2008.

4.  The Inspector General of the Marine Corps, through

scheduled command inspections, shall review command

voting assistance programs, plans, and determine whether

unit Voting Assistance Officers are appointed and

trained in accordance with MCO 1742.1A and have

sufficient supplies to provide voting assistance.

5. Commanders at all levels of command shall coordinate

information efforts.  All Commands shall conduct command

information briefing prior to primary elections to

inform and motivate military/civilian personnel and

their family members to exercise their right to vote in

primary and general elections.  Information provided

shall include dates of scheduled primaries and general

elections and state deadlines for voter registration,

absentee ballot requests, and the receipt of returned,

voted ballots.  Information programs should utilize

local websites and installation newspapers.  A

well-fixed location will be established and display

voting information along with MCVO/IVAO’s name, phone,

e-mail address, and office location.  Libraries, medical

and dental clinics, commissaries, exchanges, MWR

facilities, schools, and training facilities should be

considered as excellent places to display voting

information.

6. Ensure that a FPCA is directly delivered to all

Marines and their eligible family members, all civilian

Marines stationed overseas, and their eligible family

members by January 15, 2008.  The FPCA may be delivered

either in hand or through electronic means.  When the

FPCA is delivered, the UVAO needs to ensure that

instructions are given on the purpose and proper

completion of the FPCA.

B.  PHASE II:  Registration and Primary Elections during

Period of January - October 2008.  This phase will require

careful planning and execution of voting assistance programs

in order to inform potential voters of the primary elections

scheduled to begin in early 2008.  Commanders at all levels

of command shall:

1.  Have VAO’s attend a Voting Assistance Workshop

and will concentrate on providing absentee registration

and voting assistance to personnel and eligible family

members for Federal, state, and run-off primary

elections.

2.  Ensure that all Voting Assistance Officer have an

adequate supply of FPCA’s and FWAB’s.

2.  Ensure FPCA’s are made available to Marines,

civilian Marines, and their family members stationed

overseas by August 15, 2008.

3.  Ensure FPCA’s are made available to all eligible

voters within the United States by September 15, 2008.

4.  Conduct “Armed Forces Voters Week” (week of August

31 - September 7, 2008).  Develop programs to create

voting awareness and to motivate absentee voters to

participate in the general election.  Publicize the

importance of early action and planning well in advance

of election deadlines by the absentee voter in order to

obtain their ballot for the General Election.  Publicize

the last date before a Federal General Election that an

absentee ballot mailed from the location can reasonably

be expected to be delivered to the appropriate state and

local election officials.

5.  Conduct “Absentee Voters Week” (week of October

12-18, 2008).  Encourage all Marines and their family

Members to vote and mail their absentee ballots during

this week.

6.  Continue command information programs and

dissemination of voter information.

C.  PHASE III:  Requesting Ballots for the General Election

During Period of July – November 4, 2008.  Commanders at all

levels of command shall:

1.  Continue disseminating voting information.

2.  Ensure availability of FPCA’s and FWAB’s to eligible

voters within the United States by September 15, 2008.

3.  Communicate how and when to use the FWAB and

recommend its use if the voter meets established

criteria and does not receive the regular absentee

ballot in sufficient time to vote and return it to be

counted.

D.  PHASE IV:  Evaluation Period, November 5 – December 31,

2008).  Commanders at all levels of command shall:

1.  Assist as requested, with post-election surveys of

eligible voters.  The survey’s findings will be used in

formulating plans for future voting assistance programs.

2.  Coordinate voting information support materials with

Service Voting Action Officer (SVAO) in support of

requirements as directed by the Director, FVAP.

3.  File an “After Acton Report” by December 31, 2008

with the SVAO summarizing successes and/or problems

experienced in conduct of the program.  A checklist for

and the format of this report will be provided by the

SVAO.

V.  ESSENTIAL MATERIALS

A.  2008–09 Voting Assistance Guide (VAG 2008-09).  The

2008-09 Federal Voting Assistance Guide is the basic

reference that provides all VAO’s with the necessary

information to provide potential voters the following

assistance:

1.  Explanation of current procedures for absentee

registration and voting in each state, the District

of Columbia, the Commonwealth of Puerto Rico, and the

territories of American Samoa, Guam, and the Virgin

Islands.

2.  Absentee registration and voting deadlines

established by the states, territories, and other

jurisdictions, along with dates of primary and general

elections.

3.  Addresses, including zip codes of local election

officials in each state, territory, and other

jurisdictions.

4.  Provides guidance on the use of the FPCA.

B.  Federal Post Card Application (FPCA) for Registration

and Absentee Ballot Request (Standard Form 76).

1.  The FPCA, a postage-paid form, is authorized by law

for use by persons covered by the UOCAVA.  The FPCA was

revised in October 2005 to include more information and

to make the form more user friendly.  The previous

edition of the FPCA (Rev. 10-95) may continue to be used

until existing stocks are exhausted.  The FPCA

(Rev. 10-95) should be placed in an envelope with proper

postage affixed to protect enclosed personal information.

2.  Due to difference in the use of the FPCA by the

various states and other jurisdictions, the 2008-09

Voting Assistance Guide should be consulted to determine

how each jurisdiction authorizes use of the FPCA by

voters.

3.  FPCA’s are requisitioned in accordance with MCO

1742.1A enclosure 3 or purchased directly from the

General Services Administration (GSA).

4.  An on-line version of the FPCA that is accepted by

all 50 states, the District of Columbia and territories

is available at the Marine Corps voting Web Site

(www.manpower.usmc.mil/voting) and the FVAP Web Site

(www.fvap.gov).

a. The on-line version provides an alternative to

individuals who cannot obtain the card stock version

and must be placed in an envelope with proper

postage affixed.

C.  Federal Write-In Absentee Ballot (FWAB) (SF 186).

1.  The FWAB is authorized by law and may be used in

general elections for federal office by uniformed

service voters and by overseas voters who make timely

application for, and do not receive, regular absentee

ballots.  For those who wish to use the FWAB, the

following criteria must be met:

a.  The request for a regular absentee ballot must

have been received by the local election official at

least 30 days before the general election or the

state deadline, whichever is later.  Some states may

allow FWAB use in primary and run-off elections; see

the 2008-09 Voting Assistance Guide for details.

b.  The FWAB may be submitted by uniformed service

personnel and their family members when absent from

their voting residence and located either inside or

outside the U.S., and by other U.S. citizens when

located outside the United States.  The United

States is defined as the 50 states, the District of

Columbia, Puerto Rico, Guam, the Virgin Islands, and

American Samoa.

c.  The FWAB must be received by local election

officials no later than the deadline for receipt of

regular absentee ballots under state law.

2.  All Marine Corps installations outside the U.S.,

including Marines on naval vessels at sea, should stock

a sufficient supply of FWABs for use by voters outlined

above.  Consult the 2008-09 Voting Assistance Guide

for detailed instructions on the FWAB.

NOTE:  ONLY THOSE VOTERS WHO MAKE A TIMELY APPLICATION FOR THEIR REGULAR STATE BALLOT AND MEET ALL THE CRITERIA MAY USE A FWAB.

VI.  FVAP POINT OF CONTACTS:

Director

Federal Voting Assistance Program

Department of Defense

Washington, DC 20301-1155

Telephone number: (703) 588-1584

DSN 425-1584, 1-800-438-8683

E-mail address    vote@fvap.gov

Home Page:        www.fvap.gov

Fax number:       (703) 696-1352

Fax DSN:          426-1352

VII.  USMC VOTING POINTS OF CONTACT:

SENIOR SERVICE VOTING REPRESENTATIVE (SSVR)

Mr. Timothy R. Larsen

SERVICE VOTING ACTION OFFICER (SVAO)

Mr. David E. James

david.e.james@usmc.mil

USMC VOTING HOT LINE

mailto:mra.voting.officer@usmc.mil

DSN:  278-9511

Comm: (703) 784-9511

## MAJOR COMMAND VOTING OFFICES

MARFORCOM       Comm: (757) 836-1524      DSN: 836-1524

MARFORPAC       Comm: (808) 477-8465      DSN: (315)477-8465

MARFORRES       Comm: (504) 678-0428      DSN: 678-0428

NCR             Comm: (703) 784-2151      DSN: 278-2151

MCRC            Comm: (703) 784-9431      DSN: 278-9431

MARLOGCOM       Comm: (229) 639-5400      DSN: 567-5400

MARFOREUR       Comm: 011-49-7031-15-2902 DSN: (314)431-2902

MARFORSOUTH     Comm: (305) 437-2540      DSN: None

MARFORCENCOM    Comm: (813) 827-7022      DSN: 651-7022

MARFORKOREA     Comm:                     DSN: (315)723-7032

MARFORSTRAT     Comm: (402) 232-9280      DSN:  272-9280

MARSOC          Comm: (910) 232-9280      DSN:  751-9070